Special Event Planning Checklist

- Pick your date and location; check availability with City of Lethbridge Recreation, Parks & Culture Department

□

□

Decide on time for event (including set up and take down times)

Determine what amenities will be required for the event

- Bleachers

- Electrical Access o Water Access

o Extra Garbage Cans o PA System

o Tables o Chairs

o Extra Washrooms o Vests/Signage

o Staging o Tents

o  Picnic Shelters

- Fill out and submit Special Event Application Form to Recreation, Parks & Culture Department at least one month prior to event

- Contact first call to do locates if any structures that require staking into the ground are going to be erected

- Obtain Insurance Certificate and provide a copy to Recreation, Parks & Culture at least 2 weeks prior to event

- Compile a route/site map and provide a copy to Recreation, Parks & Culture at least 2 weeks prior to event

- Set up a site meeting (if necessary) with City of Lethbridge staff and event organizers at least 2 weeks prior to event

- Determine what other service providers you may need and contact them for help

o Police o Fire

o  Chinook Health Unit

o ALCB (Alberta Liquor Control Board) o Transit

o St. John’s Ambulance (or other first aid provider) o Security

- Ensure you have a contingency plan in place to accommodate weather which may affect your event

41